## Sheet1
Date | Note | Contributor
2022-08-05 | Added a changelog-file, altered the .gitignore according to the Kicad standard, started adding annotations to the datasheets for navigation. | Doomn00b
2022-08-11 | Changed the project to use generic links instead of local links, merged footprint libraries into one, merged symbol libraries into one, started rewriting V9990 datasheet with Open Sans font, for future open source datasheet | Doomn00b
| Changed V9990 symbol and footprint | Doomn00b
| Replaced C3 THT capacitor with SMD. | Doomn00b
2022-08-12 | Replaced RGB-connector with real VGA conn from Amphenol, changed decoupling, put power-parts on their own sheet, | Doomn00b
| Replaced big 14MHz oscillator with SMD one, | Doomn00b
| Changed the glue logic to use Advanced 74xx versions, with far higher performance. | Doomn00b
| Removed Composite video and replaced with RGB Scart | Doomn00b
2022-08-20 | Routing. Almost finished routing for the VDP. Moved back the footprint for the 14mhz oscillator to THT as it is easier to find outside US/Europe and I have a bunch laying around here. Organized all components into the PCB. Removed the holed in the cartridge so I can better measure them in the standard MSX cartridge. Changed the RGB connector footprint to a shorter version so we can fit it in the standard size cartridge. Fixed multiple footprints to 0805 as we will be standardizing in that size. | cristiano
2022-08-21 | Routing for rev 1 is done. Pending prototyping and possible fixes to the main circuit/pcb before first test batch. Waiting for review of others. | cristiano